## Gannt
Type | Item | Task Name | Stage | Work Days | Ind Start Date | Start | Finish | Hours | Predecessors | Status | Notes |  | SCROLL
| Deliverable | ReviewWIthMe Final Project |  | 106 |  | 2022-02-28 | 2022-07-28 | 302 | time axis 2022-02-28 to 2022-10-19
Phase | time axis 2022-02-28 to 2022-10-19
Task | 1.1 | 1.0 Project Setup | Setup | 18 | 2022-02-28 | 2022-02-28 | 2022-03-24 | 34 |  |  |  | 0 | 2022-02-28: Project Setup Timeline
Task | 1.2 | Initial Meeting with Capability Manager | Setup | 4 | 2022-02-28 | 2022-02-28 | 2022-03-04 | 3 |  | Complete
Milestone | 1.3 | Finalise Project Charter after Client Meeting | Setup | 1 | 2022-03-07 | 2022-03-07 | 2022-03-08 | 5 | 3 | On Track | bar: 2022-03-07 to 2022-03-08
Task | 1.4 | Create GANTT Chart | Setup | 1 | 2022-03-07 | 2022-03-07 | 2022-03-08 | 2 |  | Complete
Task | 1.5 | Create Project Scope | Setup | 3 | 2022-03-07 | 2022-03-07 | 2022-03-10 | 5 |  | Started
Task | 1.6 | Create Stake Holder Register | Setup | 3 | 2022-03-07 | 2022-03-07 | 2022-03-10 | 4 |  | Complete
Task | 1.7 | Create Power V Interest Chart | Setup | 5 | 2022-03-07 | 2022-03-07 | 2022-03-14 | 2 |  | Complete
Task | 1.8 | Create Stake Holder Communication Plan | Setup | 5 | 2022-03-14 | 2022-03-14 | 2022-03-21 | 4 |  | Complete
Task | 1.9 | Create Work Breakdown Structure | Setup | 5 | 2022-03-14 | 2022-03-14 | 2022-03-21 | 3 |  | Complete
Task | 1.1 | Create MoSCoW Chart | Setup | 5 | 44634 | 44634 | 44641 | 2 |  | started powerpoint
Phase | 1.11 | Create RACI Chart | Setup | 4 | 2022-03-20 | 2022-03-20 | 2022-03-24 | 4 |  | Complete | bar: 2022-03-21 to 2022-03-24
Task |  | 2.0 Research Question Investigation | Research | 50 | 2022-03-21 | 2022-03-21 | 2022-05-30 | 123 |  |  |  |  | 2022-03-21: Research Timeline
Task | 2.1 | Research and compare Local and Remote code review (pre-commit and CI/CD) | Research | 10 | 2022-03-21 | 2022-03-21 | 2022-04-04 | 10 |  | Not Started
Milestone | 2.2 | Research into automation chatbots and their compatibility with other software. | Research | 10 | 2022-03-21 | 2022-03-21 | 2022-04-04 | 10 |  | Not Started | bar: 2022-03-21 to 2022-04-04
Milestone | 2.3 | Research into instant messaging programs used at work e.g., Slack - and the integration with GitHooks/Github | Research | 10 | 2022-04-04 | 2022-04-04 | 2022-04-18 | 5 |  | Not Started | bar: 2022-04-04 to 2022-04-18
|  | Research into code quality | Research |  | 2022-04-04 | 2022-04-04 | 2022-04-05 | 3 |  | Not Started
Task |  | Benefits and drawbacks of code quality in terms of commits | Research |  | 2022-04-05 | 2022-04-05 | 2022-04-06 | 5 |  | Not Started
Task | 2.4 | Benefits and Drawbacks of AWS LEX in terms of speed, functionality, stability, and cost. | Research | 10 | 2022-04-04 | 2022-04-04 | 2022-04-18 | 10 |  | Not Started
Task | 2.5 | Benefits and Drawbacks of SlackBOT in terms of speed, functionality, stability, and cost. | Research | 10 | 2022-04-18 | 2022-04-18 | 2022-05-02 | 10 |  | Not Started
Task | 2.6 | Benefits and Drawbacks of AWS Chatbot in terms of speed, functionality, stability, and cost. | Research | 10 | 2022-04-18 | 2022-04-18 | 2022-05-02 | 10 |  | Not Started
Task | 2.7 | Research into GitHooks/GitHub and their usability for this project | Research | 10 | 2022-05-02 | 2022-05-02 | 2022-05-16 | 10 |  | Not Started
Task | 2.8 | Comparrison between SlackBOT, AWS Chabot, and Amazon Lex in terms of speed, functionality, stability, scalability, and cost. | Research | 10 | 2022-05-02 | 2022-05-02 | 2022-05-16 | 10 |  | Not Started
Milestone | 2.9 | Final Compilation of Research and Creation of Draft Poster | Research | 5 | 2022-05-16 | 2022-05-16 | 2022-05-23 | 10 |  | Not Started | bar: 2022-05-16 to 2022-05-23
Task | 2.1 | Refinement and creation of final Poster | Research | 5 | 2022-05-23 | 2022-05-23 | 2022-05-30 | 30 |  | Not Started
Phase |  | 3.0 Create, Test, and Deploy Application | Create | 38 | 2022-06-06 | 2022-06-06 | 2022-07-28 | 145 |  | Not Started |  |  | 2022-06-06: Project Create Timeline
Milestone | 3.1 | Setup local environment for GIT CLI | Create | 5 | 2022-06-06 | 2022-06-06 | 2022-06-13 | 15 |  | Not Started | bar: 2022-06-06 to 2022-06-13
Milestone | 3.2 | Setup JIRA | Create | 5 | 2022-06-13 | 2022-06-13 | 2022-06-20 | 5 |  | Not Started | bar: 2022-06-13 to 2022-06-20
Milestone | 3.3 | Setup a Slack channel for notification purposes and call it 'Code-Review' | Create | 5 | 2022-06-13 | 2022-06-13 | 2022-06-20 | 5 |  | Not Started | bar: 2022-06-13 to 2022-06-20
Task | 3.4 | Setup Remote 'demo' repository in GitHub (commit/push etc) | Create | 5 | 2022-06-13 | 2022-06-13 | 2022-06-20 | 15 |  | Not Started
Task | 3.5 | Configure GitHub SECRETS | Create | 10 | 2022-06-20 | 2022-06-20 | 2022-07-04 | 15 |  | Not Started
Milestone | 3.6 | Unit Test GitHub SECRETS | Create | 5 | 2022-07-04 | 2022-07-04 | 2022-07-11 | 15 |  | Not Started | bar: 2022-07-04 to 2022-07-11
|  | Configure related YAML files | Create | 5 | 2022-07-05 | 2022-07-05 | 2022-07-12 | 15 |  | Not Started
Task | 3.7 | Create and configure a CI/CD Pipeline for remote repository. | Create | 5 | 2022-07-04 | 2022-07-04 | 2022-07-11 | 15 |  | Not Started
Milestone | 3.8 | Unit Tests for CI/CD Pipeline | Create | 5 | 2022-07-11 | 2022-07-11 | 2022-07-18 | 15 |  | Not Started | bar: 2022-07-11 to 2022-07-18
Task | 3.9 | Configure and install pre-commit (and dependencies required) | Create | 5 | 2022-07-11 | 2022-07-11 | 2022-07-18 | 15 |  | Not Started
| 3.1 | Unit test pre-commits | Create | 6 | 2022-07-20 | 2022-07-20 | 2022-07-28 | 15 |  | Not Started
Key
| Milestone | ◆

## Milestones
Milestone No. | Phase | Name | Deadline | Evidence
M1 | Project Setup | Finalise Project Charter after Client Meeting | 2022-03-18 | This is the conclusion of Task 1 and will involve a completed project charter and all supporting documentation i.e. RACI, MOSCOW et. Al.
M2 | Project Research | Research into automation chatbots and their compatibility with other software. | 2022-04-15 | Research notes and final thoughts of which chatbot service will provide the best outcome (suitability, price, compatabiltiy)
M3 | Project Research | Research into instant messaging programs used at work e.g., Slack - and the integration with GitHooks/Github | 2022-05-13 | Research notes and final thoughts about which instant messaging programs will provide the best outcome (suitability, price, compatibility)
M4 | Project Research | Research poster | 2022-05-27 | Draft and final versions of research poster, replete with 5+ references and bibliography
M5 | Project Create | Setup local environment for GIT CLI | 2022-06-17 | Setup a local folder structure environment for the code-review project.
M6 | Project Create | Setup JIRA | 2022-07-15 | Setup JIRA environment for the code-review project.
M7 | Project Create | Setup a Slack channel for notification purposes and call it 'Code-Review' | 2022-07-29 | Setup a Slack channel environment for the code-review project.
M8 | Project Create | Unit Test GitHub SECRETS | 2022-07-11
M9 | Project Create | Unit Tests for CI/CD Pipeline | 2022-07-18