## RACI Template
OnBoardWithMe RACI Chart | Supervisor | Project Client | Project Technical Lead | Test User #1 | Test User #2 | Project Technical Lead | Supervisor | tester
Project task or deliverable | External Resources | Project Leadership | Project Team Members |  |  | Onboarding Team
1.0 Project Setup
Initial Meeting with Capability Manager | - | C | R,A | R | R | R,A | R | R
Finalise Project Charter after Client Meeting | A | I | R,A | R | R | R,A | R | R
Create GANTT Chart | - | C | R,A | R | R | R,A | R | R | >
Create Project Scope | - | C | R,A | R | R | R,A | R | R
Create Stake Holder Register | - | C | R,A | R | R | R,A | R | R
Create Power V Interest Chart | - | C | R,A | R | R | R,A | R | R
Create Stake Holder Communication Plan | - | C | R,A | R | R | R,A | R | R
Create Work Breakdown Structure | - | C | R,A | R | R | R,A | R | R
Create MoSCoW Chart | - | C | R,A | R | R | R,A | R | R
Create RACI Chart | - | C | R,A | R | R | R,A | R | R
2.0 Research Question Investigation
Research and compare Local and Remote code review (pre-commit and CI/CD) | - | - | R,A | R | R | R,A | R | R
Research into automation chatbots and their compatibility with other software. | - | - | R,A | R | R | R,A | R | R
Research into instant messaging programs used at work e.g., Slack - and the integration with GitHooks/Github | - | - | R,A | R | R | R,A | R | R
Research into code quality | - | - | R,A | R | R | R,A | R | R
Benefits and drawbacks of code quality in terms of commits | - | - | R,A | R | R | R,A | R | R
Benefits and Drawbacks of AWS LEX in terms of speed, functionality, stability, and cost. | bar: - A - - - - - - - - to C I C C C C C C C C; R R R R R R R R R R to R R R R R R R R R R; R R R R R R R R R R to R R R R R R R R R R
Benefits and Drawbacks of SlackBOT in terms of speed, functionality, stability, and cost. | - | - | R,A | R | R | R,A | R | R
Benefits and Drawbacks of AWS Chatbot in terms of speed, functionality, stability, and cost. | - | - | R,A | R | R | R,A | R | R
Research into GitHooks/GitHub and their usability for this project | - | - | R,A | R | R | R,A | R | R
Comparrison between SlackBOT, AWS Chabot, and Amazon Lex in terms of speed, functionality, stability, scalability, and cost. | - | - | R,A | R | R | R,A | R | R
Final Compilation of Research and Creation of Draft Poster | - | I | R,A | R | R | R,A | R | R
Refinement and creation of final Poster | - | - | R,A | R | R | R,A | R | R
3.0 Create, Test, and Deploy Application
Setup local environment for GIT CLI |  | I | R,A | R | R | R,A | R | R
Setup JIRA | - | I | R,A | R | R | R,A | R | R
Setup a Slack channel for notification purposes and call it 'Code-Review' | - | I | R,A | R | R | R,A | R | R
Setup Remote 'demo' repository in GitHub (commit/push etc) | - | - | R,A | R | R | R,A | R | R
Configure GitHub SECRETS | - | - | R,A | R | R | R,A | R | R
Unit Test GitHub SECRETS | - | I |  | R | R |  | R | R
Configure related YAML files | - | - | R,A | R | R | R,A | R | R
Create and configure a CI/CD Pipeline for remote repository. | - | - | R,A | R | R | R,A | R | R
Unit Tests for CI/CD Pipeline | - | I | R,A | R | R | R,A | R | R
Configure and install pre-commit (and dependencies required) | - | - | R,A | R | R | R,A | R | R
Unit test pre-commits | - | - | R,A | R | R | R,A | R | R

## Sheet2
BAE RACI Chart | Supervisor | Project Client | Project Technical Lead | Test User #1 | Test User #2
Project task or deliverable | External Resources | Project Leadership | Project Team Members
Initiate Phase Returns |  |  | - | - | -
Submit Project Request | A | I | - | - | -
Request Review by PMO | A | I | - | - | -
Research Solution | A | I | - | - | -
Develop Business Case | A | I | - | - | -
Plan Phase Activities |  | I | - | - | -
Create Project Charter | A | I | - | - | -
Create Project Schedule | A | I | - | - | -
Create Additional Plans as required | A | I | - | - | -
Execute Phase Activities
Build deliverables | A | - | - | - | -
Daily Team Standups | - | - |  | A
Create Status Report | A | - | - | - | -
Initial Service Offering Template |  |  | - | - | -
Draft Templates | - | - | - | A | C
Review Draft Document | - | - | - | I | C
Approval for Service Offering Template | - | - | I | I | A, C
Priority of Applications by MVP
Meeting with DXC Lead to review list of Applications |  | - | C | A | C
Meeting with Sponsor to understand the Sponsors view of Applications | C | - | I | A | I
Identify the 34 applications "In Scope" | A | - | I | I | I
Applications based on priority (MVP) | A | - | I | I | I
Applications that are NON-MVP | A | - | I | I | I
Applications "Out of Scope" | A | - | I | I | I
MVP (Priority) Applications (12)
Meeting with MVP Application Team |  | - | I | A | -
Draft Application Service Offering Template for MVP | - | - | I | I | -
Approval of Service Offering document by MVP team | - | - | I | I | -
Approval of Service Offering document by Tech Lead | - | - | I | A | C
Lessons Learnt | - | - | - | A | C
Remaining, NON-MVP Applications (22)
Meeting with NON-MVP Application Team | - | C | I | A | -
Draft Application Service Offering Template | - | - | I | I | -
Approval of Service Offering document by Application team | - | A, R | I | I | -
Approval of Service Offering document by Tech Lead | - | - | I | A | C
Lessons Learnt | - | - | - | A | C
Control Phase Activities
Escalate issues | - | - | I | A | -
Perform Change Management | - | - | I | A | -
Close Phase Activities
Create Lessons Learned | - | - |  |  | C
Create Project Closure Report | - | - | A | I
Handle Service Offering documents and transfer these to NAGIOS Monitoring | - | - | I | A | C

## RACI Example
RACI CHART TEMPLATE |  | Build better gantt charts with TeamGantt for FREE!
Project task or deliverable | Project manager | Strategist | Designer | Front-end developer | Back-end developer
Design sitemap | C | R | A | I | I
Design wireframes | C | A | R | I | I
Create style guide | A | C | R | C | I
Code templates | A | I | C | R | C

## RACI Definitions
Responsible | This team member does the work to complete the task. Every task needs at least one Responsible party, but it’s okay to assign more.
Accountable | This person delegates work and is the last one to review the task or deliverable before it’s deemed complete. On some tasks, the Responsible party may also serve as the Accountable one. Just be sure you only have one Accountable person assigned to each task or deliverable. (Note: It might not be your PM!)
Consulted | Every deliverable is strengthened by review and consultation from more than one team member. Consulted parties are typically the people who provide input based on either how it will impact their future project work or their domain of expertise on the deliverable itself.
Informed | These team members simply need to be kept in the loop on project progress, rather than roped into the details of every deliverable.

## RACI assignment drop-down data
R | This worksheet is purely admnistrative. The letters in column A feed the formula that auto-populates the RACI assignment drop-down on other tabs. Making changes here could impact the formula on your RACI Template and RACI Example worksheets.
A
C
I