## Task Decomposition
Task Id | Task Name | Start | Deadline | Hours | Factors/Risks Affecting Hours | Deliverable | Example/Attachment
1.0 Project Setup
1.1 | Initial Meeting with Capability Manager | 2022-02-28 | 2022-03-05 | 3 | Complexity of Ask, GDPR Requirements, Client discussions. | Draft version of Project Charter, Meeting Transcript/Notes/Email communication | Proje
1.2 | Finalise Project Charter after Client Meeting | 2022-02-28 | 2022-03-05 | 5 | Last minute changes to project, Requirements. | Final Project Charter, Meeting Transcript/Notes/Email communication
1.3 | Create Stakeholder Register | 2022-03-07 | 2022-03-11 | 2 | Changes to Stakeholders. | Stakeholder Register, Meeting Transcript/Notes/Email communication
1.4 | Create RACI Chart | 2022-03-07 | 2022-03-11 | 2 | Changes to EPES Project Team, Holidays of team members etc. | RACI Chart, Meeting Transcript/Notes/Email communication
1.5 | Create MoSCoW Chart | 2022-03-14 | 2022-03-18 | 4 | Discussion with client leading to differences of opinion on mandatory requirements. | MoSCoW Chart, Meeting Transcript/Notes/Email communication
1.6 | Create EMV Risk Chart | 2022-03-14 | 2022-03-18 | 4 | Identifying risks. Being able to cost risks based on current operation. GDPR restrictions. | EMV Risk Chart, Meeting Transcript/Notes/Email communication
2.0 Research Question Investigation
2.1 | Research into Cloud vs OnPrem vs Hyrbid Infrastructure in terms of speed, functionality, stability and scalability and cost. | 2022-03-21 | 2022-04-01 | 15 | Availability of Research, Time needed to understand and follow up on research. | Research notes and references. ~1000 word research blog
2.2 | Benefits and Drawbacks of SQL Databases in terms of speed, functionality, stability and scalability and cost | 2022-03-21 | 2022-04-01 | 20 | Availability of Research, Time needed to understand and follow up on research. | Research notes and references. ~1000 word research blog
2.3 | Benefits and Drawbacks of NoSQL Databases in terms of speed, functionality, stability and scalability and cost | 2022-04-04 | 2022-04-15 | 20 | Availability of Research, Time needed to understand and follow up on research. | Research notes and references. ~1000 word research blog
2.4 | Benefits and Drawbacks of Amazon RDS in terms of speed, functionality, stability and scalability and cost | 2022-04-04 | 2022-04-15 | 20 | Availability of Research, Time needed to understand and follow up on research. | Research notes and references. ~1000 word research blog
2.5 | Benefits and Drawbacks of Amazon Aurora in terms of speed, functionality, stability and scalability and cost | 2022-04-18 | 2022-04-29 | 20 | Availability of Research, Time needed to understand and follow up on research. | Research notes and references. ~1000 word research blog
2.6 | Benefits and Drawbacks of Amazon DynamoDB in terms of speed, functionality, stability and scalability and cost | 2022-04-18 | 2022-04-29 | 20 | Availability of Research, Time needed to understand and follow up on research. | Research notes and references. ~1000 word research blog
2.7 | Comparison between Aurora, RDS, DynamoDB in terms of speed, functionality, stability and scalability and cost | 2022-05-02 | 2022-05-13 | 20 | Availability of Research, Time needed to understand and follow up on research. | Research notes and references. ~1000 word research blog
2.8 | Methodologies of Migrating Databases to AWS including speed, functionality, stability, scalability and cost | 2022-05-02 | 2022-05-13 | 20 | Availability of Research, Time needed to understand and follow up on research. | Research notes and references. ~1000 word research blog
2.9 | Final Compilation of Research and Creation of Draft Poster | 2022-05-16 | 2022-05-20 | 30 | Availability of Research, Time needed to understand and follow up on research. | A1 sized Research Poster replete with 5+ References and Bibliography
2.1 | Refinement and creation of final Poster | 2022-05-23 | 2022-05-27 | 30 | Availability of Research, Time needed to understand and follow up on research. | A1 sized Research Poster replete with 5+ References and Bibliography
3.0 Create and Deploy AWS Infrastructure and Databases
3.1 | Setup and configure AWS environment for project. | 2022-06-06 | 2022-06-10 | 5 | Accessability of AWS infrastructure, understanding and learning curve of using AWS services. | Fully configured AWS environment suitable for the project.
3.2 | Configure UAC and levels of access with user accounts. | 2022-06-06 | 2022-06-10 | 5 | Accessability of AWS infrastructure, understanding and learning curve of using AWS services. | Multiple user accounts with correct levels of access.
3.3 | Configure VPC and Availability Zones | 2022-06-13 | 2022-06-17 | 5 | Accessability of AWS infrastructure, understanding and learning curve of using AWS services. | Fully configured VPC for the project with multiple AZ's for data redundancy.
3.4 | Design high level architecture for EPES system | 2022-06-13 | 2022-06-17 | 10 | Accessability of AWS infrastructure, understanding and learning curve of using AWS services. | High level architecture diagram with detailed explanation and notes.
3.5 | Write code to create and deploy database to AWS cloud | 2022-06-20 | 2022-07-01 | 15 | Accessability of AWS infrastructure, understanding and learning curve of using AWS services. | Python code.
3.6 | Unit test database creation code | 2022-07-04 | 2022-07-08 | 15 | Accessability of AWS infrastructure, understanding and learning curve of using AWS services. | Unit testing code and output.
3.7 | Populate Database with test/dummy data | 2022-07-11 | 2022-07-15 | 15 | Accessability of AWS infrastructure, understanding and learning curve of using AWS services. | Python code.
3.8 | Create Lambdas to action SQL Agent Jobs for daily maintenance | 2022-07-11 | 2022-07-15 | 15 | Accessability of AWS infrastructure, understanding and learning curve of using AWS services. | Unit testing code and output.
3.9 | Write API scripts to CRUD to the database, making use of the Lambdas | 2022-07-18 | 2022-07-22 | 20 | Accessability of AWS infrastructure, understanding and learning curve of using AWS services. | Python code.
3.1 | Unit test API Scripts | 2022-07-25 | 2022-07-29 | 15 | Accessability of AWS infrastructure, understanding and learning curve of using AWS services. | Unit testing code and output.
3.11

## Deliverables
Del. No. | Name | Deadline
D1 | Draft version of Project Charter | 2022-03-05
D2 | Final Project Charter | 2022-03-05
D4 | Stakeholder Register | 2022-03-11
D5 | RACI Chart | 2022-03-11
D6 | MoSCoW Chart | 2022-03-18
D7 | EMV Risk Chart | 2022-03-18
D8 | Research Notes for Research subtask 2.1 | 2022-04-01
D9 | Research Notes for Research subtask 2.2 | 2022-04-01
D10 | Research Notes for Research subtask 2.3 | 2022-04-15
D11 | Research Notes for Research subtask 2.4 | 2022-04-15
D12 | Research Notes for Research subtask 2.5 | 2022-04-29
D13 | Research Notes for Research subtask 2.6 | 2022-04-29
D14 | Research Notes for Research subtask 2.7 | 2022-05-13
D15 | Research Notes for Research subtask 2.8 | 2022-05-13
D16 | Draft Poster | 2022-05-20
D17 | Final Poster | 2022-05-27
D18 | Configured AWS environment for EPES | 2022-06-10
D19 | User Accounts created for different levels of user: Scanner, Admin, Maintenance, Testing | 2022-06-10
D20 | Configured VPC for EPES Environment | 2022-06-17
D21 | High level architecture showing proposed EPES cloud infrastructure | 2022-06-17
D22 | Python script to create and deploy databases to EPES Cloudpsace | 2022-07-01
D23 | Unit Tests of Database Code | 2022-07-08
D24 | Dummy Data entered into Databases | 2022-07-15
D25 | Lambdas for 5 primary EPES maintenance tasks | 2022-07-15
D26 | API Scripts for access to the Database | 2022-07-22
D27 | Unit tests for API scripts | 2022-07-29

## Milestones
Milestone No. | Name | Deadline | Evidence
M1 | Initial project charter and suporting documentation created and approved by client/sponsor | 2022-03-18 | This is the conclusion of Task 1 and will involve a completed project charter and all supporting documentation i.e. RACI, MOSCOW et. Al.
M2 | Research into Hybrid vs Cloud vs OnPrem | 2022-04-01 | Research Notes and final thoughts on best fit solution for EPES
M3 | Research into the different types of database | 2022-04-15 | Research notes about the differences between NoSQL and SQL Databases and final thoughts on best approach for EPES
M4 | Research into the different AWS services available for databases | 2022-05-13 | Research notes about the different services available and a comparison between them in terms of cost, scalability etc. Final thoughts on best approach for EPES
M5 | Research poster | 2022-05-27 | Draft and final versions of research poster, replete with 5+ references and bibliography
M6 | Configured AWS environment for EPES project | 2022-06-17 | AWS VPC and configured user accounts for the EPES project
M7 | Created, deployed and populated databases for EPES in the VPC cloud environment | 2022-07-15 | Python code that has been written, tested and deployed to AWS in order to create and populate requisite EPES database in the cloud environment
M8 | Lambdas and API scripts for using and communicating with the database | 2022-07-29 | Python code that has been written, tested and deployed to AWS to CRUD and maintain the EPES databases via the API gateway

## Schedule
| March | [30 empty] | April | [29 empty] | May | [30 empty] | June | [29 empty] | July | [30 empty] | August
| T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5
Major Task 1 | March F: D1, D2; March F: D3,D4; March F: D5,D6 M1
Major Task 2 | April F: D7, D8 M2; April F: D9, D10 M3; April F: D11, D12; May F: D13, D14 M4; May F: D15; May F: D16 M5
Major Task 3 | June F: D17, D18; June F: D19, D20 M6; July F: D21; July F: D22; July F: D23, D24 M7; July F: D25; July F: D26 M8